## Read Me
NIST CSF 2.0 Risk Assessment
Northbridge Kitchen Supply Co. — Companion Workbook
Prepared July 2026 · Fictional exercise, built for portfolio purposes
Fictional company notice
Northbridge Kitchen Supply Co. is a fictional company invented for this self-directed exercise. No real organization was assessed, and no finding in this workbook describes a real entity or real data.
What this workbook contains
Function Summary — the maturity heatmap by CSF Function, matching the executive report.
Risk Register — all 35 assessed subcategories at full detail: current state, target state, gap, likelihood, impact, risk score, finding, recommendation, owner, and remediation horizon.
Roadmap — the same 35 actions grouped into 30/90/180-day horizons.
Scoping approach
NIST CSF 2.0 defines 106 subcategories across 6 Functions and 22 Categories. Scoring all 106 at full depth isn't realistic for a first-pass assessment, so this exercise selected 35 representative subcategories, weighted proportionally to each Function's share of the full framework — a standard time-boxing approach for an initial assessment.
Maturity scale (Current State & Target State)
0 — Not Implemented: no process, control, or practice exists.
1 — Partially Implemented: informal, inconsistent, or undocumented practice exists.
2 — Largely Implemented: a defined practice exists and is followed most of the time.
3 — Fully Implemented: a documented, consistently-followed, and periodically reviewed practice.
Risk scoring model
Each gap between Current and Target state is assessed for risk using Likelihood x Impact (1-5 each), producing a Risk Score from 1-25:
Likelihood (1-5): how probable it is this gap leads to a real security event within the next 12 months.
Impact (1-5): how severe the consequence would be if it did — financial, operational, legal, or reputational.
Risk bands: 15-25 = Critical ¦ 10-14 = High ¦ 5-9 = Medium ¦ 1-4 = Low
Owners
Every recommendation is assigned to whichever role at a 42-person, no-in-house-security company would realistically execute it: the Ops Manager (who covers IT part-time), the outsourced MSP (helpdesk and technical execution), or Leadership (strategic and policy decisions only leadership can make).
Source
Subcategory identifiers and descriptions are drawn from the official NIST CSF 2.0 Core (NIST, published Feb 26, 2024). Current state, target state, likelihood, impact, findings, and recommendations are this assessment's own analysis of the fictional Northbridge environment.

## Risk Register
Function | Category | Subcategory ID | Subcategory Description | Current State | Current State Label | Target State | Target State Label | Gap | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Band | Finding | Recommendation | Owner | Horizon (Days)
Govern | Organizational Context (GV.OC) | GV.OC-01 | The organizational mission is understood and informs cybersecurity risk management | 1 | Partially Implemented | 2 | Largely Implemented | 1 | 4 | 3 | 12 | High | No written statement ties cybersecurity priorities to business objectives, so risk decisions get made ad hoc without a shared reference point. | Draft a 1-page cybersecurity risk statement tied to business priorities. | Leadership | 30
Govern | Risk Management Strategy (GV.RM) | GV.RM-01 | Risk management objectives are established and agreed to by organizational stakeholders | 0 | Not Implemented | 1 | Partially Implemented | 1 | 3 | 4 | 12 | High | Leadership has never formally agreed on what level of risk is acceptable for Northbridge, so there's no shared basis for risk decisions. | Hold a leadership session to agree on 3-5 risk management objectives. | Leadership | 30
Govern | Roles, Responsibilities, and Authorities (GV.RR) | GV.RR-01 | Organizational leadership is responsible and accountable for cybersecurity risk and fosters a culture that is risk-aware, ethical, and continually improving | 1 | Partially Implemented | 2 | Largely Implemented | 1 | 3 | 4 | 12 | High | Nobody has clearly documented who owns cybersecurity. It defaults informally to the Ops Manager without a defined mandate. | Document a RACI matrix for security tasks across Ops Manager, MSP, and IT contractor. | Leadership | 30
Govern | Cybersecurity Supply Chain Risk Management (GV.SC) | GV.SC-01 | A cybersecurity supply chain risk management program, strategy, objectives, policies, and processes are established and agreed to by organizational stakeholders | 0 | Not Implemented | 2 | Largely Implemented | 2 | 4 | 4 | 16 | Critical | No strategy for managing risk from suppliers (3PL, hosting, Salesforce, Stripe) -- Northbridge trusts its vendors by default. | Build a vendor list with a one-page risk note per supplier. | Ops Manager | 30
Govern | Organizational Context (GV.OC) | GV.OC-03 | Legal, regulatory, and contractual requirements regarding cybersecurity -- including privacy and civil liberties obligations -- are understood and managed | 0 | Not Implemented | 1 | Partially Implemented | 1 | 3 | 4 | 12 | High | Nobody has catalogued which legal, contractual, or regulatory cybersecurity obligations actually apply (e.g. state breach-notification laws, PCI obligations via Stripe). | Compile an inventory of regulatory and contractual cybersecurity obligations. | Ops Manager | 90
Govern | Policy (GV.PO) | GV.PO-01 | Policy for managing cybersecurity risks is established based on organizational context, cybersecurity strategy, and priorities and is communicated and enforced | 0 | Not Implemented | 2 | Largely Implemented | 2 | 4 | 3 | 12 | High | There's no written acceptable-use or data-handling policy -- expectations for staff exist only informally. | Adopt and distribute an acceptable-use and data-handling policy. | Leadership | 90
Govern | Cybersecurity Supply Chain Risk Management (GV.SC) | GV.SC-04 | Suppliers are known and prioritized by criticality | 0 | Not Implemented | 1 | Partially Implemented | 1 | 3 | 4 | 12 | High | Vendors aren't tiered by criticality, so a compromised low-risk tool gets the same lack of scrutiny as Salesforce or Stripe. | Tier vendors into Critical vs Standard risk. | Ops Manager | 90
Govern | Risk Management Strategy (GV.RM) | GV.RM-03 | Cybersecurity risk management activities and outcomes are included in enterprise risk management processes | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 3 | 6 | Medium | Cybersecurity risk isn't factored into broader business risk conversations -- it lives in its own silo, when it has any home at all. | Define a written risk tolerance statement so risk decisions have a consistent reference point. | Leadership | 180
Govern | Oversight (GV.OV) | GV.OV-01 | Cybersecurity risk management strategy outcomes are reviewed to inform and adjust strategy and direction | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 3 | 6 | Medium | Leadership has no standing review of cybersecurity posture, so nothing prompts a reassessment as the business changes. | Add a standing leadership review of cybersecurity posture (e.g. quarterly). | Leadership | 180
Govern | Cybersecurity Supply Chain Risk Management (GV.SC) | GV.SC-06 | Planning and due diligence are performed to reduce risks before entering into formal supplier or other third-party relationships | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 2 | 4 | Low | New vendors are onboarded without any cybersecurity due diligence. | Add a lightweight security questionnaire to vendor onboarding before signing new suppliers. | Ops Manager | 180
Identify | Asset Management (ID.AM) | ID.AM-01 | Inventories of hardware managed by the organization are maintained | 1 | Partially Implemented | 2 | Largely Implemented | 1 | 3 | 4 | 12 | High | Hardware inventory exists only informally through the MSP's ticketing history -- there's no authoritative, current device list. | Validate a complete hardware asset inventory via the MSP. | MSP | 90
Identify | Asset Management (ID.AM) | ID.AM-02 | Inventories of software, services, and systems managed by the organization are maintained | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 3 | 6 | Medium | No consolidated list of the SaaS applications actually in use (M365, Salesforce, Stripe, WooCommerce, and whatever else staff have signed up for). | Build a single SaaS application inventory. | Ops Manager | 30
Identify | Asset Management (ID.AM) | ID.AM-07 | Inventories of data and corresponding metadata for designated data types are maintained | 0 | Not Implemented | 2 | Largely Implemented | 2 | 4 | 5 | 20 | Critical | No inventory of where customer PII and payment data actually lives or flows. | Map where customer PII and payment data flows end to end. | Ops Manager | 30
Identify | Risk Assessment (ID.RA) | ID.RA-01 | Vulnerabilities in assets are identified, validated, and recorded | 0 | Not Implemented | 2 | Largely Implemented | 2 | 4 | 4 | 16 | Critical | The customer-facing ordering portal has never been vulnerability-scanned. | Commission a basic external vulnerability scan of the ordering portal. | MSP | 90
Identify | Risk Assessment (ID.RA) | ID.RA-05 | Threats, vulnerabilities, likelihoods, and impacts are used to understand inherent risk and inform risk response prioritization | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 2 | 4 | Low | Even when a gap is found, there's no consistent way to weigh how likely and how damaging it actually is -- prioritization is gut-feel. | Formally use this year's findings to prioritize next year's risk response, rather than starting from scratch. | Ops Manager | 180
Identify | Risk Assessment (ID.RA) | ID.RA-08 | Processes for receiving, analyzing, and responding to vulnerability disclosures are established | 0 | Not Implemented | 1 | Partially Implemented | 1 | 1 | 3 | 3 | Low | If a security researcher found a flaw in the ordering portal today, there's no published way for them to responsibly report it. | Publish a responsible-disclosure contact so researchers have a way to report vulnerabilities. | Ops Manager | 180
Identify | Improvement (ID.IM) | ID.IM-01 | Improvements are identified from evaluations | 0 | Not Implemented | 1 | Partially Implemented | 1 | 1 | 2 | 2 | Low | Nothing captures lessons learned after a near-miss or a vendor's security incident -- the same gaps could resurface unnoticed. | Make this risk assessment an annual, repeatable process so improvements get tracked year over year. | Ops Manager | 180
Protect | Identity Management, Authentication, and Access Control (PR.AA) | PR.AA-01 | Identities and credentials for authorized users, services, and hardware are managed by the organization | 2 | Largely Implemented | 2 | Largely Implemented | 0 | 4 | 3 | 12 | High | Account and credential management for M365, Salesforce, and the 3PL system relies on default settings rather than a deliberate process -- no consistent on/offboarding discipline. | Document an offboarding checklist for M365, Salesforce, and 3PL access. | Ops Manager | 30
Protect | Identity Management, Authentication, and Access Control (PR.AA) | PR.AA-02 | Identities are proofed and bound to credentials based on the context of interactions | 1 | Partially Implemented | 3 | Fully Implemented | 2 | 4 | 4 | 16 | Critical | MFA is not enforced for all M365 accounts, including remote staff. | Enforce MFA for all M365 accounts via Conditional Access. | MSP | 30
Protect | Awareness and Training (PR.AT) | PR.AT-01 | Personnel are provided with awareness and training so that they possess the knowledge and skills to perform general tasks with security risks in mind | 0 | Not Implemented | 2 | Largely Implemented | 2 | 5 | 3 | 15 | Critical | Staff have never received phishing-awareness training. | Roll out annual phishing-awareness training to all staff. | Ops Manager | 90
Protect | Data Security (PR.DS) | PR.DS-01 | The confidentiality, integrity, and availability of data-at-rest are protected | 1 | Partially Implemented | 2 | Largely Implemented | 1 | 3 | 5 | 15 | Critical | Encryption of stored customer and payment data has never been verified. | Confirm encryption-at-rest practices with Stripe, the 3PL, and the web host in writing. | MSP | 90
Protect | Platform Security (PR.PS) | PR.PS-01 | Configuration management practices are established and applied | 0 | Not Implemented | 2 | Largely Implemented | 2 | 4 | 4 | 16 | Critical | No confirmed process for keeping the WooCommerce/WordPress portal patched. | Confirm a monthly patch cadence for the WooCommerce/WordPress portal. | MSP | 90
Protect | Platform Security (PR.PS) | PR.PS-04 | Log records are generated and made available for continuous monitoring | 1 | Partially Implemented | 2 | Largely Implemented | 1 | 3 | 3 | 9 | Medium | It's unclear whether M365 audit logs are enabled and retained long enough to be useful during an investigation. | Confirm M365 audit logging is enabled and retained 90+ days. | MSP | 90
Protect | Technology Infrastructure Resilience (PR.IR) | PR.IR-04 | Adequate resource capacity to ensure availability is maintained | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 2 | 4 | Low | Nobody has confirmed the hosting provider's capacity plan -- a traffic spike could take the ordering portal down with no defined response. | Confirm the hosting provider's SLA and scaling plan can handle a traffic spike or attack. | MSP | 180
Detect | Continuous Monitoring (DE.CM) | DE.CM-01 | Networks and network services are monitored to find potentially adverse events | 0 | Not Implemented | 1 | Partially Implemented | 1 | 4 | 4 | 16 | Critical | No monitoring in place to notice a compromise while it's happening. | Close monitoring gaps with the MSP for adverse-event detection. | MSP | 90
Detect | Continuous Monitoring (DE.CM) | DE.CM-09 | Computing hardware and software, runtime environments, and their data are monitored to find potentially adverse events | 0 | Not Implemented | 1 | Partially Implemented | 1 | 3 | 3 | 9 | Medium | Servers, endpoints, and the applications running on them aren't monitored for the kind of anomalies that would flag a compromise in progress. | Enable monitoring for unauthorized changes to servers, endpoints, and the software running on them. | MSP | 180
Detect | Adverse Event Analysis (DE.AE) | DE.AE-02 | Potentially adverse events are analyzed to better understand associated activities | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 2 | 4 | Low | Even if something unusual were noticed, there's no defined way to analyze it and decide whether it's actually a problem. | Define what counts as an investigable incident and how it gets triaged. | MSP | 180
Detect | Adverse Event Analysis (DE.AE) | DE.AE-03 | Information is correlated from multiple sources | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 2 | 4 | Low | Signals from different systems (M365, the portal, the 3PL) are never correlated, so a coordinated attack could look like several unrelated blips. | Correlate signals across M365, the portal, and the 3PL so related events aren't missed. | MSP | 180
Respond | Incident Management (RS.MA) | RS.MA-01 | The incident response plan is executed in coordination with relevant third parties once an incident is declared | 0 | Not Implemented | 2 | Largely Implemented | 2 | 5 | 3 | 15 | Critical | No written incident response plan exists. | Draft a 2-page incident response plan. | Ops Manager | 90
Respond | Incident Response Reporting and Communication (RS.CO) | RS.CO-02 | Internal and external stakeholders are notified of incidents | 0 | Not Implemented | 2 | Largely Implemented | 2 | 3 | 5 | 15 | Critical | No process for notifying customers or regulators after a breach. | Identify breach-notification requirements and add timelines to the IR plan. | Ops Manager | 90
Respond | Incident Management (RS.MA) | RS.MA-03 | Incidents are categorized and prioritized | 0 | Not Implemented | 1 | Partially Implemented | 1 | 3 | 3 | 9 | Medium | If multiple things went wrong at once, there's no defined way to decide what to tackle first. | Add severity tiers to the incident response plan so the team knows what to tackle first. | Ops Manager | 180
Respond | Incident Mitigation (RS.MI) | RS.MI-01 | Incidents are contained | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 2 | 4 | Low | There's no playbook for containing an active incident -- the first response would be improvised. | Add concrete containment steps to the incident response plan. | MSP | 180
Recover | Incident Recovery Plan Execution (RC.RP) | RC.RP-01 | The recovery portion of the incident response plan is executed once initiated from the incident response process | 0 | Not Implemented | 1 | Partially Implemented | 1 | 3 | 4 | 12 | High | There's no recovery plan to execute -- Northbridge would be figuring out restoration steps live, during an actual outage. | Add a recovery plan section to the incident response plan, with clear restoration steps. | Ops Manager | 180
Recover | Incident Recovery Plan Execution (RC.RP) | RC.RP-03 | The integrity of backups and other restoration assets is verified before using them for restoration | 0 | Not Implemented | 1 | Partially Implemented | 1 | 3 | 3 | 9 | Medium | Backups may exist through the hosting provider or 3PL, but nobody has ever tested whether they'd actually restore cleanly. | Test-restore backups at least annually to confirm they actually work. | MSP | 180
Recover | Incident Recovery Communication (RC.CO) | RC.CO-03 | Recovery activities and progress in restoring operational capabilities are communicated to designated internal and external stakeholders | 0 | Not Implemented | 1 | Partially Implemented | 1 | 2 | 2 | 4 | Low | There's no template for telling customers what's happening during an outage or breach -- messaging would be improvised under pressure. | Add a customer-facing outage communication template. | Ops Manager | 180

## Function Summary
Maturity Heatmap by Function
All formulas reference the Risk Register tab directly — update a score there and this table recalculates.
Function | Subcategories | Avg Current (0-3) | Avg Target (0-3) | Gap | Critical | High | Medium | Low
Govern | 10 | 0.2 | 1.4 | 1.2 | 1 | 6 | 2 | 1
Identify | 7 | 0.14286 | 1.4286 | 1.2857 | 2 | 1 | 1 | 3
Protect | 7 | 0.71429 | 2 | 1.2857 | 4 | 1 | 1 | 1
Detect | 4 | 0 | 1 | 1 | 1 | 0 | 1 | 2
Respond | 4 | 0 | 1.5 | 1.5 | 2 | 0 | 1 | 1
Recover | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 1
All Functions | 35 | 0.22857 | 1.4571 | 1.2286 | 10 | 9 | 7 | 9
Note: Redder Gap cells = larger distance between current and target maturity. Source: this assessment's Risk Register tab.

## Roadmap
Remediation Roadmap
Grouped by effort/dependency horizon, not just severity -- matches the executive report.
Quick Wins — 30 Days (8 actions)
Function | ID | Recommendation | Owner | Risk Band
Govern | GV.OC-01 | Draft a 1-page cybersecurity risk statement tied to business priorities. | Leadership | High
Govern | GV.RM-01 | Hold a leadership session to agree on 3-5 risk management objectives. | Leadership | High
Govern | GV.RR-01 | Document a RACI matrix for security tasks across Ops Manager, MSP, and IT contractor. | Leadership | High
Govern | GV.SC-01 | Build a vendor list with a one-page risk note per supplier. | Ops Manager | Critical
Identify | ID.AM-02 | Build a single SaaS application inventory. | Ops Manager | Medium
Identify | ID.AM-07 | Map where customer PII and payment data flows end to end. | Ops Manager | Critical
Protect | PR.AA-01 | Document an offboarding checklist for M365, Salesforce, and 3PL access. | Ops Manager | High
Protect | PR.AA-02 | Enforce MFA for all M365 accounts via Conditional Access. | MSP | Critical
Medium-Term — 90 Days (12 actions)
Function | ID | Recommendation | Owner | Risk Band
Govern | GV.OC-03 | Compile an inventory of regulatory and contractual cybersecurity obligations. | Ops Manager | High
Govern | GV.PO-01 | Adopt and distribute an acceptable-use and data-handling policy. | Leadership | High
Govern | GV.SC-04 | Tier vendors into Critical vs Standard risk. | Ops Manager | High
Identify | ID.AM-01 | Validate a complete hardware asset inventory via the MSP. | MSP | High
Identify | ID.RA-01 | Commission a basic external vulnerability scan of the ordering portal. | MSP | Critical
Protect | PR.AT-01 | Roll out annual phishing-awareness training to all staff. | Ops Manager | Critical
Protect | PR.DS-01 | Confirm encryption-at-rest practices with Stripe, the 3PL, and the web host in writing. | MSP | Critical
Protect | PR.PS-01 | Confirm a monthly patch cadence for the WooCommerce/WordPress portal. | MSP | Critical
Protect | PR.PS-04 | Confirm M365 audit logging is enabled and retained 90+ days. | MSP | Medium
Detect | DE.CM-01 | Close monitoring gaps with the MSP for adverse-event detection. | MSP | Critical
Respond | RS.MA-01 | Draft a 2-page incident response plan. | Ops Manager | Critical
Respond | RS.CO-02 | Identify breach-notification requirements and add timelines to the IR plan. | Ops Manager | Critical
Long-Term — 180 Days (15 actions)
Function | ID | Recommendation | Owner | Risk Band
Govern | GV.RM-03 | Define a written risk tolerance statement so risk decisions have a consistent reference point. | Leadership | Medium
Govern | GV.OV-01 | Add a standing leadership review of cybersecurity posture (e.g. quarterly). | Leadership | Medium
Govern | GV.SC-06 | Add a lightweight security questionnaire to vendor onboarding before signing new suppliers. | Ops Manager | Low
Identify | ID.RA-05 | Formally use this year's findings to prioritize next year's risk response, rather than starting from scratch. | Ops Manager | Low
Identify | ID.RA-08 | Publish a responsible-disclosure contact so researchers have a way to report vulnerabilities. | Ops Manager | Low
Identify | ID.IM-01 | Make this risk assessment an annual, repeatable process so improvements get tracked year over year. | Ops Manager | Low
Protect | PR.IR-04 | Confirm the hosting provider's SLA and scaling plan can handle a traffic spike or attack. | MSP | Low
Detect | DE.CM-09 | Enable monitoring for unauthorized changes to servers, endpoints, and the software running on them. | MSP | Medium
Detect | DE.AE-02 | Define what counts as an investigable incident and how it gets triaged. | MSP | Low
Detect | DE.AE-03 | Correlate signals across M365, the portal, and the 3PL so related events aren't missed. | MSP | Low
Respond | RS.MA-03 | Add severity tiers to the incident response plan so the team knows what to tackle first. | Ops Manager | Medium
Respond | RS.MI-01 | Add concrete containment steps to the incident response plan. | MSP | Low
Recover | RC.RP-01 | Add a recovery plan section to the incident response plan, with clear restoration steps. | Ops Manager | High
Recover | RC.RP-03 | Test-restore backups at least annually to confirm they actually work. | MSP | Medium
Recover | RC.CO-03 | Add a customer-facing outage communication template. | Ops Manager | Low